## To Do
Project Charter-VCT Traceability System
Sr# | Activity | PLANNED |  | ACTUAL |  | Status | Responsibility | Remarks
|  | From Date | To Date | From Date | To Date
1 | Database Installation on the server | 2023-08-17 | 2023-08-17 |  |  | Pending | SATO / Denso | SQL Database should be installed on the server by ISD Team
2 | Application hosting on the server | 2023-08-17 | 2023-08-17 |  |  | Pending | SATO / Denso | VCT-Dashboard Web application hosting on the same or anyother server
3 | Scheduler Installation on the Laptop | 2023-08-17 | 2023-08-17 |  |  | Pending | SATO / Denso | Required help ISD Team to install the application
4 | VCT Lot Entry Application Installtion | 2023-08-17 | 2023-08-17 |  |  | Pending | SATO / Denso | Required help ISD Team to install the application